**Advisory for Compliance of Condition Subsequent (Financial Closure) under GNA Regulations, 2022.**

1. An applicant which is REGS (other than Hydro generating station), ESS (excluding PSP), or Renewable power park developer to which an in-principle grant of connectivity has been issued shall achieve the financial closure for the capacity of such Connectivity, latest by 6 months prior to the scheduled date of a commercial operation or start date of Connectivity of such applicant, whichever is later.
2. Regulation 11A further provides that any extension in the timeline to achieve the milestone of Financial Closure due to extension in SCOD by the REIA shall not be allowed more than 12 months from the original timeline as per initial SCOD. Accordingly, CTU shall not extend the due date to achieve the financial closure (in case of extension in SCOD by REIA for applicants granted connectivity on LoA/PPA route), for a period beyond 12 months
3. In terms of the mandate of Regulation 11A (*Conditions subsequent to be satisfied by the Connectivity Grantee*) of the GNA Regulations, 2022, the applicants shall submit the following documents to demonstrate the achievement of financial closure to CTU within 15 days of achievement of financial closure: -
4. Undertaking for achievement of financial closure in the format available on CTUIL’s website.
5. Board Resolution regarding authorization of the person submitting the affidavit.
6. **In case of loan from financial institution:**
* **Sanction letter** from the loan issuing entity(ies) specifically agreeing to finance the project for which connectivity has been granted;
* **Duly acknowledged** by the Connectivity grantee **or** proof of first disbursement;
1. **In case of loan from Parent / Group company:**
* Board Resolution from parent/group company or Inter-corporate loan agreement towards disbursal of loan for the project for which Connectivity is granted.
* Board resolution of the Connectivity grantee regarding request/acceptance of the funds.
* Net Worth Certificate of entity infusing funds from Chartered Accountant **or** latest audited financial statements of the entity infusing funds.
1. **In case of funding from Connectivity Grantee;**
* Board Resolution of Connectivity Grantee towards the amount to be funded by the Connectivity Grantee clearly mentioning the name of the project.
* Net Worth Certificate of Connectivity Grantee from Chartered Accountant or latest audited financial statements of Connectivity Grantee.
1. **In case of equity infusion from Shareholders:**
* Board Resolution of entity infusing equity;
* Board Resolution of the Connectivity grantee towards acceptance of above referred funding;
* Net Worth Certificate from Chartered Accountant of the entity infusing equity or latest audited financial statements of the parent company.
* Share-holding pattern of the Connectivity grantee/subsidiary.
1. **In case of funds through VGF/Any other grant from Government**:.
* Approval letter from government.
1. **In case of funds through ISAs/ other bilateral arrangements between Generators and Park Developers**:.
* ISA Agreements of all the generators
* Proof/Supporting Documents/CA Certificate for funds received as ISA Charges from the Generators. OR

Board Resolution and Net Worth Certificate of all the Generators signing the ISA.

1. **Timelines: -** upon submission of the documents by the applicants in support of achievement of financial closure, CTU shall scrutinise the documents on fortnightly basis and shall inform deficiencies/clarifications, if any, to the applicant for rectification/clarification. The applicants shall rectify/clarify the same within a period of 7 working days [from the date of the receipt of CTU’s email]. Thereafter, CTU on being satisfied with the documents in support of financial closure, shall issue confirmation regarding achievement of the financial closure in terms of the GNA Regulations, 2022. In case of non-achievement of financial closure or non-submission of documents in support of financial closure, CTU shall administer the same in terms of Regulation 11B of the GNA Regulations, 2022.

Timeline

|  |  |  |
| --- | --- | --- |
| Sl. No. | **Milestone** | **Timeline** |
| 1. | Achievement of FC by the Grantee | Latest by 6 months prior to the scheduled date of a commercial operation or start date of Connectivity, whichever is later |
| 2. | Submission of FC Documents to CTU | Within 15 days of achieving the financial closure |
| 3. | Scrutiny of Documents by CTUIL | CTU shall scrutinise the documents on fortnightly basis and shall inform deficiencies/clarifications, if any, to the applicant for rectification/clarification |
| 4.  | Clarification by Applicant on observations by CTU | Within Seven working days of the receipt of the mail from CTUIL. |

\**Option for submission of clarification and submission of related documents shall be given to applicant only once after scrutiny of the documents by CTU.*

1. **Benchmark for Project Cost for different types of Projects/Parks: -** The Project Cost for different types of Projects/Parks varies across locations. Accordingly, it has been proposed that Applicant shall submit the Project Cost in the undertaking considering the per MW cost requirement for different type of RE Projects as below –

|  |  |
| --- | --- |
| **Type of project** | **Cost (Rs. Crore/MW)** |
| Wind | 7 |
| Solar | 5 |
| BESS | 4 |
| Park  | 0.35 |

UD\_FC (Format of the FC Undertaking) mentioning the project cost less than the above per MW cost shall not be accepted for compliance of Reg. 11A of the GNA Regulations, 2022.