

Application For Milestone Extension under CERC Order dated 14.08.2026 in Petition No. 5/SM/2026
	LEFT: Field Name
	RIGHT: Information


[Original App. No. 22xxxxxxxx]
	FIELD NAME
	DETAILS

	A. APPLICANT & CONNECTIVITY DETAILS 

	1. Original Application ID
	

	2. Name of Applicant / Entity
	

	3. Date of In-principle grant of Connectivity
	

	4. Date of Final grant of Connectivity
	

	5. Connectivity Quantum (MW)
	

	6. Installed Capacity (MW)
	Solar:
Wind:
ESS MW:
ESS MWh:

	7. Connectivity Route / Category
	Land / Land-BG / LoA or PPA

	8. GNA Effectiveness Date
	

	B. MILESTONE(S) FOR WHICH ADDITIONAL TIME IS SOUGHT 

	9. Milestone(s) for extension
	Tick any one:
(a) Land Documents - Regulation 11A(1)
(b) Financial Closure - Regulation 11A(2)
(c) COD - Regulation 24.6

	10. Original Compliance Due date (as per GNA Regulations)
	(should be minimum 15 days from date of application)

	11. Total Land Required for Project Capacity (Acres)
	(Minimum: Solar – 3 Acres/MW, Wind – 0.25 Acre/MW, ESS – 1.2 Acres/100MWh)

	C. LAND DOCUMENT / FINANCIAL CLOSURE MILESTONE - REGULATION 11A(1)/11A(2)  —  Fill only when Land Documents OR Financial Closure is ticked at Sl. No. 8

	12. Land Documents already submitted (Acres)
	

	13. Additional Land Documents being furnished with this request (Acres)
	

	14. Cumulative Eligible Land (%)
	[((Sl. No. 12 + Sl. No. 13) / Sl. No. 11) x 100, should be >= 20%]

	15. Copy of Land documents
	Attached (Yes/No)

	16. FORMAT-TITLE-REPORT
	Attached (Yes/No)

	17. FORMAT-UD-LAND
	Attached (Yes/No)

	D. COD MILESTONE - REGULATION 24.6  —  Fill only when COD is ticked at Sl. No. 8

	18. Connectivity Quantum for which CoD extension is sought (MW)
	

	19. Land Documents already submitted (Acres)
	

	20. Additional Land Documents being furnished with this request (Acres)
	

	21. Cumulative Eligible Land (%)
	[(Sl. No. 19 + Sl. No.20) / Sl. No. 11] x 100,
should be >= 75% if “Land” OR “Land BG” at Sl. No. 7,
should be >= 50% if “LoA or PPA” at Sl. No. 7

	22. Copy of Land documents
	Attached (Yes/No)

	23. FORMAT-TITLE-REPORT
	Attached (Yes/No)

	24. FORMAT-UD-LAND
	Attached (Yes/No)

	25. Contract Details - Major / Key Equipment
	Attached (Yes/No)

	26. Contract Details - Civil Works
	Attached (Yes/No)

	27. Contract Details - Electrical Works
	Attached (Yes/No)

	28. EPC Contract (if applicable)
	Attached (Yes/No)

	E. DETAILS OF BANK ACCOUNT FOR REFUND OF MEC

	29. Beneficiary Account Number
	

	30. Beneficiary Account Name
	

	31. IFSC Code
	

	32. Bank Name
	

	33. Branch Name
	

	F. APPLICANT DECLARATIONS & SUBMISSION

	34. Declaration - Information / Documents
	I declared that the information and attached documents are true, complete and relate to the selected Connectivity grant.

	35. Declaration - MEC
	I acknowledge that extension is optional and subject to eligibility and payment of applicable MEC. The maximum extension period shall be as permissible under CERC Order.

	36. Declaration - Firm Start Date & Mismatch Charges
	I acknowledge that additional time does not change firm start date and applicable mismatch charges under Sharing Regulations, 2020 continue.

	37. Declaration - PPA / Cost & Risk
	I acknowledge that additional time is at my own cost and risk and does not modify, dilute or override PPA terms.

	38. Declaration – Eligibility Scrutiny & Deficiency Rectification
	I acknowledge that CTUIL shall scrutinize the documents within 7 working days and intimate deficiencies, if any, which the Applicant shall rectify within a further 7 working days, failing which no additional time shall be granted, and the Applicant shall be required to comply with the timelines originally prescribed under the GNA Regulations.


*All fields are Mandatory

	Submission Date:
	

	
	Signature:

Name:
Designation:
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