**सेंट्रल ट्रांसमिशन यूटिलिटी ऑफ इंडिया लिमिटेड**

**CENTRAL TRANSMISSION UTILITY OF INDIA LIMITED**

**(Wholly Owned Subsidiary of Power Grid Corporation of India Limited)**

**(A Government of India Enterprise)**

**REQUEST FOR PROPOSAL (RfP)**

**(Section – I: Request for Proposal)**

**for**

**Appointment of Independent Engineer for “Eastern Region Expansion Scheme-XXXIX (ERES-XXXIX)”**

**(Spec. No. CTUIL/IE/2024-25/61/R1)**

(This document is meant for exclusive purpose of bidding against this specification only and shall not be transferred, reproduced or otherwise used for purpose other than that for which it is specifically issued)

**REQUEST FOR PROPOSALS (RfP)**

(**Domestic Competitive Bidding**)

**(SINGLE STAGE TWO ENVELOPE BIDDING)**

DATE **:**  **06.02.2025**

FUNDING : **DOMESTIC**

1. This Request for Proposal (RfP) for the subject package have been published on **06.02.2025** on CTUIL’s website, GeM(Government e-marketplace) portal (link provided at para 9.0 below) and on Government of India’s Central Public Procurement Portal (<https://eprocure.gov.in>). Any Corrigendum and/or amendments, etc. shall also be published only on the above website/portals.
2. Central Transmission Utility of India Limited (CTUIL), (wholly Owned Subsidiary of Power Grid Corporation of India Limited) a Government of India Enterprise incorporated under the Companies Act, 2013, having its Registered Office at “Saudamini”, Plot No.-2, Sector 29, Gurgaon-122001, Haryana (hereinafter referred to as ‘CTUIL’/’Owner’/’Employer’) has decided to engage an **Appointment of Independent Engineer for “Eastern Region Expansion Scheme-XXXIX (ERES-XXXIX)”.**
3. **Scope of work:**

3.1 The detailed scope of work and deliverables covered under the subject package **Appointment of Independent Engineer for “Eastern Region Expansion Scheme-XXXIX (ERES-XXXIX)”** are given in Section – II: Terms of Reference (ToR) of the Bidding Documents for following Transmission Scheme:

**Scope of Work of the Transmission Scheme:**

| **Sl. No.** | **Name of Transmission Element** | **Scheduled COD in months from Effective date** |
| --- | --- | --- |
|  | Establishment of new 765/400kV, 2x1500MVA GIS substation at Gopalpur in Odisha   * 765/400kV, 1500MVA ICTs: 2 nos. (7x500MVA single phase units including one spare) * 765kV ICT bays: 2 nos. * 400kV ICT bays: 2 nos. * 765kV, 330 MVAr Bus reactor: 2 nos. (7x110MVAr single phase units including one spare unit for both bus and line reactors) * 765kV Bus reactor bays: 2 nos. * 420kV, 125MVAr Bus reactor: 2 nos. * 400kV Bus reactor bays: 2 nos. * 765kV line bays: 2 nos.   *[for termination of Angul (POWERGRID) – Gopalpur 765kV D/c line along with 765kV, 1x330MVAr switchable line reactor at Gopalpur end in both circuits]*   * 400kV line bays: 2 nos.   *[for termination of Gopalpur – Gopalpur (OPTCL) 400kV D/c (Quad) line]*   * 765kV, 330MVAr (3x110MVAr single phase units) switchable line reactor along with associated bay and 500ohm NGR (with NGR bypass arrangement) *[at Gopalpur end in both circuits of Angul (POWERGRID) – Gopalpur 765kV D/c line]*: 2 nos.   **Additional space for future expansion**:   * 765/400kV, 4x1500MVA ICTs (12x500MVA single phase units) along with associated ICT bays at both voltage levels * 400/220kV, 4x500MVA ICTs along with associated ICT bays at both voltage levels * 765kV, 2x330MVAr (6x110MVAr single phase units) bus reactor along with associated bays * 420kV, 2x125MVAr bus reactor along with associated bays * 8 nos. of 765kV line bays (along with space for switchable line reactor) for future lines * 10 nos. of 400kV line bays (along with space for switchable line reactor) for future lines * 12 nos. of 220kV line bays for future lines * 765kV bus sectionaliser bay: 1 set * 400kV bus sectionaliser bay: 1 set * 220kV bus sectionaliser bay :1 set * 220kV bus coupler bay: 2 no. | **31.12.2027**  **(38 Months)** |
|  | Angul – Gopalpur 765kV D/c line   * Line Length (Approx.): 200 kms |
|  | Extension at 765kV level at Angul (POWERGRID) S/s including bus extension in GIS   * *765kV AIS line bays (along with space for future switchable line reactor): 2 nos. [for termination of Angul (POWERGRID) – Gopalpur 765kV D/c line] including bus extension in GIS of about 3000m* |
|  | Gopalpur – Gopalpur (OPTCL) 400kV D/c (Quad) line   * Line Length (Approx.): 25 kms |
|  | Extension at 400kV level at Gopalpur (OPTCL) GIS S/s  400kV GIS line bays: 2 nos. *[for termination of Gopalpur – Gopalpur (OPTCL) 400kV D/c (Quad) line]* + 2 nos. for diameter completion |

The detailed **Qualifying Requirements (QR) and Technical Evaluation Criteria** have been provided in the Bidding Document.

1. The **completion period** for the subject packages shall be the period as specified in Special Conditions of Contract (Section – IV) of the bidding documents.
2. CTUIL intends to use **domestic funding** for eligible payments under the contract for the packages mentioned above.
3. CTUIL, therefore, invites Proposals through GeM portal for **Appointment of Independent Engineer for “Eastern Region Expansion Scheme-XXXIX (ERES-XXXIX)”** on Domestic Competitive Bidding basis for engagement of Independent Engineer using **Quality and Cost Based Section (QCBS)** procedures under secured e-procurement procedure.

The following documents constitute the RfP document to enable Bidders to submit their Proposals:

1. Section – I: Request for Proposals;
2. Section – II: Terms of Reference (ToR);
3. Section – III: Conditions of Contract;
4. Section – IV: Special Conditions of Contract;
5. Section– V: Proposal Forms (Technical & Financial), Attachments & Schedule

7.1 This Request for Proposals extended through media, website, written communication or by any other means, and issuance of RfP Documents shall not be construed to mean that the prospective Bidders to whom the Request for Proposal has been extended and/or RfP Documents have been issued is deemed to be an eligible Bidder. The eligibility of the Bidders shall be determined as per the provisions of RfP Documents.

7.2 Bidding will be conducted through Open Tender bidding procedures as per the provisions of RfP Documents and the contract shall be executed as per the provisions of the Contract. The respective rights of the Employer and the Independent Engineer shall be governed by the RfP Documents.

1. The complete Bidding Documents are available on GeM portal <https://bidplus.gem.gov.in/all-bids> . Interested bidders shall download the Bidding Documents from the GeM portal, as per the provisions available therein.

Bidders shall ensure that their bids, complete in all respects, are submitted online through said Portal only. No DEVIATION in this regard is acceptable.

1. Interested bidders have to necessarily register themselves on the GeM portal <https://mkp.gem.gov.in/registration/signup#!/seller> to participate in the bidding under this Request for Proposal.

Bidders are advised to start the registration process on the e-Procurement Portal, as it may take a few days so as to avoid any delay in bid submission (upload) stage. Bidders may visit/communicate to GeM helpdesk regarding any query related to GeM portal.

It shall be the sole responsibility of the interested bidders to get themselves registered at the aforesaid portal and for any assistance during bid submission, system settings etc. for which they are required to contact GeM helpdesk: <https://gem.gov.in/contactUs>

**Toll Free Numbers (Inbound): Call**

**1800-419-3436 / 1800-102-3436**

**(9:00 am - 10:00 pm Mon to Sat )**

**HelpDesk Outbound No's : 07556681401, 07556685120, 01169095625**

**Railway Helpline: 011-44022666**

**Defence Helpline: 0755-6681450**

*Email:* [helpdesk-gem@gov.in](mailto:helpdesk-gem@gov.in)

**HelpDesk Walk-In Address: 2nd Floor, Jeevan Tara Building, 5-Sansad Marg, Near Patel Chowk, New Delhi-110001**

They may obtain further information regarding this RfP from the office of Manager/ Engineer, CTUIL at the address given at **para 14.0** below from 15:00 hours to 17:00 hours on all working days.

For proper uploading of the proposals on the portal namely *https://gem.gov.in/ (hereinafter referred to as the ‘portal’)*, it shall be the sole responsibility of the bidders to apprise themselves adequately regarding all the relevant procedures and provisions as detailed at the portal as well as by contacting **GeM portal** directly, as and when required, for which contact details are mentioned above. The Employer in no case shall be responsible for any issues related to timely or properly uploading/submission of the bid in accordance with the relevant provisions of the Bidding Documents.

1. A **Single Stage Two Envelope Bidding Procedure** will be adopted and will proceed as detailed in the Bidding Documents.
2. **e-Reverse Auction (e-RA)**

The electronic Reverse Auction (e-RA) is not applicable.

1. A **pre-bid meeting** will be held on **13.02.2025 at 1100 Hrs. (IST)** to clarify the bidder’s various issues raised in accordance with clause **5.2** of Section – III: Conditions of Contracts.
2. **Soft Copy Part of the Proposals** must be uploaded under Single Stage Two Envelope Bidding Procedure on the GeM portal at or before **15:00 hours** on **20.02.2025.** The e-Procurement system would not allow any late submission of proposals through the portal after the due date & time as specified.

**Hard Copy Part of the Proposals** must be submitted under Single Stage Two Envelope Bidding Procedure at the address given at para 14.0 below at or before **15:00 hours on 20.02.2025**. Late submission of proposals shall not be allowed.

First Envelope i.e., Techno-Commercial Part shall be opened on **20.02.2025** in the presence of the bidders’ representatives who choose to attend in person at the address at para 15.0 below at **15:30 hours** or may be viewed by the bidders by logging in to the portal. Second Envelope i.e., Price Part of qualified bidders shall be opened in the presence of the bidders’ representatives who choose to attend at the time and date and at the address given in the intimation for opening of Second Envelope through GeM portal itself in accordance with **Clause 21.0 of Section – III: Conditions of Contracts** or may be viewed by the bidders by logging in to the GeM portal.

All proposals must be accompanied by **Proposal Security in line with Clause 11.0 of Section-III/Section-IV of Bidding Document.** Proposal Securities must be submitted either in physical form or paid online.

Proposal Securities, Integrity Pact, Power of Attorney must be submitted in physical form or documentary evidence of online payment of the specified amount to CTUIL at the address given at para 14.0 below on or before **15:00 hours on 20.02.2025**. CTUIL shall not be responsible for any postal delay in respect of submission of hard copy part of the bids.

1. CTUIL reserves the right to cancel/withdraw this Request for Proposals without assigning any reason and shall bear no liability whatsoever consequent upon such a decision.
2. All correspondence with regards to the above shall be to the following address:

(By Post/In Person)

Central Transmission Utility of India Limited

(A wholly owned subsidiary of POWERGRID)

10th floor, IRCON International Tower-1, Plot No. 16

Sector-32, Gurugram – 122001, Haryana

Kind Attention: Mr. Rahul (Manager, C&M-CTUIL /

Mr. Mool Chand khichar (Engineer, C&M-CTUIL)

Mobile: +91-9205472328/9799211471

Email:  [rahul.prasad@powergrid.in](mailto:dwaipayan@powergrid.in);  [moolchandkh@powergrid.in](mailto:%20moolchandkh@powergrid.in)

***Note: Bidders may download the word file of the RfP document from CTUIL Portal.***

**----- *End of RfP* ----**